## Introduction
Project Name |  |  | PO3_DGW
Ref Document |  | CYRS
Ref Version |  | V0.4
Auther |  | Tarek Sharaby
Last update |  | 23/2/2020
History
Version | Author |  | Date | Change
0.1 | T.Sharaby |  | 30/01/2020 | Initial creation
0.2 | T.Sharaby |  | 2020-09-02 | Add one point and update the status for each req
0.3 | T.Sharaby |  | 23/2/2020 | Update resolved points
0.4 | Mariam El-Shakafi |  | 28/2/2020 | Added review points to CYRS V0.5

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
30/01/2020 | T.Sharaby | V0.1 | CYRS | Page 1 | Document status table : you should put the status of the document which exist in the start in a table , this table holds the following info "Document name , Suther , Version , Auther , Last update Date" | Accepted | Resolved
|  |  |  | Page 1 | I can find 2 names on the document and I don't know what the role of each one | Accepted | Resolved
30/01/2020 | T.Sharaby | V0.1 | CYRS | Document History | First creation should be draft and after the cross review is done and points fixed then it could be proposed , because as I can see both version are without status - Document history has to be at the start | Accepted | Resolved |  | Accepted
30/01/2020 | T.Sharaby | V0.1 | CYRS | ALL | The product context in terms of systme blocks should be exist in the document | Accepted | Resolved |  | Refused
30/01/2020 | T.Sharaby | V0.1 | CYRS | ALL | The design and and impelementation caonstraints , this section is for what as system wise you you don't mention this you just make the CYRS and HIS_ and software layer design comes when you make the GDD , and also the HW compoenents selection is not a constrain | Accepted | Resolved | 9/2/2020 - Mariam El-Shakafi: Hardware constraints section was moved to HSI document. Is this point still an issue?
30/01/2020 | T.Sharaby | V0.1 | CYRS | Sec 3.1 | FUNC_PO3_DGW_CYRS_01_V01 : system req doesn't mention what software shall do , istead it just descrip with system want to do then SRS descrip how to make this in terms of software specs Ex : you can say when mode is stopwatch and mode cahnged or at the power up the system dispaly the time with formate : xxxx | Accepted | Resolved |  | Open
30/01/2020 | T.Sharaby | V0.1 | CYRS | ALL | all req of system has to be reconsidered from the prospective mentioned above is to descrip the system not the software | Accepted | Resolved |  | Resolved
30/01/2020 | T.Sharaby | V0.1 | CYRS | ALL | FUNC_PO3_DGW_CYRS_02_V01: Ex : you can divid this req into : - When mode is time watch , hours , mintues , and AM/PM can be adjusted and select between them with selection button "Func1" - When mintue is selected and increment button is pressed "Func2" it should be incremented by 1 - and so on like this | Accepted | Resolved
2020-09-02 | T.Sharaby | V0.4 | CYRS | ALL | Contradiction between Status table and table of history , the last change change is different "3/2/2020 or 4/2/2020"? | Accepted | Resolved
28/2/2020 | Mariam | V0.5 | CYRS | 3.1.2 | The user cannot adjust time in any mode (only in display time mode). So, remove this requirement. Instead, use 2 requirements: - If MODE button is pressed while adjusting time in display time mode, changes should be saved and user shall return to display time mode. (replacing req. 3.1.13) - If MODE button is pressed while setting alarm in alarm time mode, alarm settings should be saved and user shall return to display time mode. (replacing req. 3.1.23) |  | Open |  | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
28/2/2020 | Mariam | V0.5 | CYRS | 3.1.6, 3.1.7 | Merge those into 1 requirement: In Display Time mode, when hours’ field is selected, FUNC2 button is used to increment hours up to 12 then back to 1. |  | Open |  | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open
28/2/2020 | Mariam | V0.5 | CYRS | 3.1.8, 3.1.9 | Same as above |  | Open
28/2/2020 | Mariam | V0.5 | CYRS | 3.1.10, 3.1.11 | Same as above |  | Open
28/2/2020 | Mariam | V0.5 | CYRS | 3.1.16, 3.1.17 | Same as above |  | Open
28/2/2020 | Mariam | V0.5 | CYRS | 3.1.18, 3.1.19 | Same as above |  | Open
28/2/2020 | Mariam | V0.5 | CYRS | 3.1.20, 3.1.21 | Same as above |  | Open
28/2/2020 | Mariam | V0.5 | CYRS | 3.1.24 | Remove this requirement (Instead: edit requirement 3.1.26 which has the same meaning). |  | Open
28/2/2020 | Mariam | V0.5 | CYRS | ALL | Add a requirement to disable alarm. Add a requirement for the initial state of alarm (which is disabled according to SIQ). |  | Open
28/2/2020 | Mariam | V0.5 | CYRS | 3.1.14 | According to SIQ, when user changes mode to alarm, they'll immediately be taken to setting alarm. Hence, this requirement is not valid. Instead, it should mention: The system shows the alarm time in HH:MM:SS AM/PM format when current mode is Display Time mode and mode is changed. |  | Open