## Schedule
Digital Watch - Project Plan
Author: Mariam El-Shakafi
Task | Owner | Expected Start Date | Epected End Date | Actual Start Date | Actual End Date | Status | Comments |  | Not started
CYRS | Bassem, Mohamed | 21/1/2020 | 23/1/2020 | 23/1/2020 | 25/1/2020 | Done |  | Initiation Phase | Working
SIQ | Mariam | 21/1/2020 | 22/1/2020 | 23/1/2020 | 24/1/2020 | Done |  |  | Have Problems
SRS | Ghada, Amr | 23/1/2020 | 24/1/2020 | 25/1/2020 | 30/1/2020 | Done |  |  | Done
HSI | Mohamed | 23/1/2020 | 24/1/2020 | 25/1/2020 | 2020-04-02 | Done
RTM | Mariam | 23/1/2020 | 24/1/2020 | 25/1/2020 | 30/1/2020 | Done
CYRS Document Update | Bassem | 2020-03-02 | 2020-04-02 | 2020-03-02 | 2020-04-02 | Done
CYRS & HSI Review | Mariam | 2020-04-02 | 2020-04-02 | 2020-05-02 | 2020-05-02 | Done
SRS Document Update | Ghada | 2020-04-02 | 2020-05-02 |  |  | Not started | Waiting for CYRS & HSI
SRS Document Review | Amr | 2020-05-02 | 2020-05-02 |  |  | Not started | Waiting for SRS
RTM Update | Mariam | 2020-06-02 | 2020-06-02 |  |  | Not started | Waiting for Released docs