## Schedule
Digital Watch - Project Plan
Author: Mariam El-Shakafi
Task | Owner | Expected Start Date | Epected End Date | Actual Start Date | Actual End Date | Status | Comments |  | Not started
CYRS | Bassem, Mohamed | 21/1/2020 | 23/1/2020 | 23/1/2020 | 25/1/2020 | Done |  | Initiation Phase | Working
SIQ | Mariam | 21/1/2020 | 22/1/2020 | 23/1/2020 | 24/1/2020 | Done |  |  | Have Problems
SRS | Ghada, Amr | 23/1/2020 | 24/1/2020 | 25/1/2020 |  | Working |  |  | Done
HSI | Mohamed | 23/1/2020 | 24/1/2020 | 25/1/2020 |  | Working
RTM | Mariam | 23/1/2020 | 24/1/2020 | 25/1/2020 |  | Working