## Introduction
Project Name |  |  | PO3_DGW
Ref Document |  | CYRS
Ref Version |  | V0.4
Auther |  | Tarek Sharaby
Last update |  | 23/2/2020
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 30/01/2020 | Initial creation
0.2 | T.Sharaby |  | 2020-09-02 | Add one point and update the status for each req
0.3 | T.Sharaby |  | 23/2/2020 | Update resolved points

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
30/01/2020 | T.Sharaby | V0.1 | CYRS | Page 1 | Document status table : you should put the status of the document which exist in the start in a table , this table holds the following info "Document name , Suther , Version , Auther , Last update Date" | Accepted | Resolved
|  |  |  | Page 1 | I can find 2 names on the document and I don't know what the role of each one | Accepted | Resolved
30/01/2020 | T.Sharaby | V0.1 | CYRS | Document History | First creation should be draft and after the cross review is done and points fixed then it could be proposed , because as I can see both version are without status - Document history has to be at the start | Accepted | Resolved |  | Accepted
30/01/2020 | T.Sharaby | V0.1 | CYRS | ALL | The product context in terms of systme blocks should be exist in the document | Accepted | Resolved |  | Refused
30/01/2020 | T.Sharaby | V0.1 | CYRS | ALL | The design and and impelementation caonstraints , this section is for what as system wise you you don't mention this you just make the CYRS and HIS_ and software layer design comes when you make the GDD , and also the HW compoenents selection is not a constrain | Accepted | Resolved | 9/2/2020 - Mariam El-Shakafi: Hardware constraints section was moved to HSI document. Is this point still an issue?
30/01/2020 | T.Sharaby | V0.1 | CYRS | Sec 3.1 | FUNC_PO3_DGW_CYRS_01_V01 : system req doesn't mention what software shall do , istead it just descrip with system want to do then SRS descrip how to make this in terms of software specs Ex : you can say when mode is stopwatch and mode cahnged or at the power up the system dispaly the time with formate : xxxx | Accepted | Resolved |  | Open
30/01/2020 | T.Sharaby | V0.1 | CYRS | ALL | all req of system has to be reconsidered from the prospective mentioned above is to descrip the system not the software | Accepted | Resolved |  | Resolved
30/01/2020 | T.Sharaby | V0.1 | CYRS | ALL | FUNC_PO3_DGW_CYRS_02_V01: Ex : you can divid this req into : - When mode is time watch , hours , mintues , and AM/PM can be adjusted and select between them with selection button "Func1" - When mintue is selected and increment button is pressed "Func2" it should be incremented by 1 - and so on like this | Accepted | Resolved
2020-09-02 | T.Sharaby | V0.4 | CYRS | ALL | Contradiction between Status table and table of history , the last change change is different "3/2/2020 or 4/2/2020"? | Accepted | Resolved
[9 empty] | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open