## Schedule
Digital Watch - Project Plan
Author: Mariam El-Shakafi
Task | Description | Owner | Expected Start Date | Epected End Date | Actual Start Date | Actual End Date | Status | Comments |  | Not started
Write CYRS document | 1. Read CRS carefully, then Create initial draft for CYRS. 2. Pass inquiries about CRS to Mariam to be handled in SIQ sheet. | Bassem, Mohamed | 21/1/2020 | 23/1/2020 | 23/1/2020 | 25/1/2020 | Done |  | Initiation Phase | Working
Write SIQ sheet | 1. Create a template for SIQ. 2. Gather inquiries from team members. | Mariam | 21/1/2020 | 22/1/2020 | 23/1/2020 | 24/1/2020 | Done |  |  | Have Problems
Write SRS document | 1. Create initial draft for SRS based on current CYRS draft. 2. Pass inquiries about CRS/CYRS to Mariam to be handled in SIQ sheet. | Ghada, Amr | 23/1/2020 | 24/1/2020 | 25/1/2020 | 30/1/2020 | Done |  |  | Done
HSI | 1. Create initial draft for HSI. 2. Pass inquiries about CRS to Mariam to be handled in SIQ sheet. | Mohamed | 23/1/2020 | 24/1/2020 | 25/1/2020 | 2020-04-02 | Done
RTM | Create an initial template for RTM, based on current CYRS and SRS drafts. | Mariam | 23/1/2020 | 24/1/2020 | 25/1/2020 | 30/1/2020 | Done
CYRS Document Update | Edit CYRS based on Eng. Tarek's review sheet. | Bassem | 2020-03-02 | 2020-04-02 | 2020-03-02 | 2020-04-02 | Done
CYRS & HSI Review | Check CYRS and HSI to make sure they are compatible with their respective review sheets, edit if necessary. | Mariam | 2020-04-02 | 2020-04-02 | 2020-05-02 | 2020-05-02 | Done
SRS Document Update | Edit SRS based on Eng. Tarek's review sheet. | Ghada | 2020-04-02 | 2020-05-02 | 2020-06-02 | 13/2/2020 | Done
SRS Document Review | 1. Add context diagram to SRS. 2. Check SRS to make sure it is compatible with its review sheet, edit document if necessary. | Amr | 2020-05-02 | 2020-05-02 | 13/2/2020 | 19/2/2020 | Done
SRS Document Update | Fix document problems (Organize SRS points, so that they're compatible with covered CYRS points). | Mariam | 20/2/2020 | 20/2/2020 | 20/2/2020 | 20/2/2020 | Done
RTM Update | Use SRS V0.6, and CYRS V0.4 to update RTM. | Mariam | 20/2/2020 | 20/2/2020 | 20/2/2020 | 20/2/2020 | Done